Z-COP August 30 – September 3, 2026 · Implementation Guide for National Focal Points Convened by The Global Call · Policy layer: MESA Institute · Action platform: On My Way

WHAT THIS IS

The Z-COP is a five-day annual summit to assess needs, design methods to solve problems, prepare organisations, and practise the implementation paths we are proposing — while demonstrating what results-first development gatherings can generate when they are built on respect, coordination, and the belief that the people closest to the problems are best placed to solve them

THE THREE-PLATFORM PIPELINE

| PLATFORM | ROLE IN THE PIPELINE |
| --- | --- |
| The Global Call | — Deploys national insight collection across 170+ countries — Coordinates focal points and contributors — Publishes pre-COP insight reports — Amplifies hub action pages and connects hubs to peer networks across the global network — Hosts relay session post-HLPF — Shares monthly recap: updates on national leadership progress |
| MESA Institute | — Sends structured policy asks to hubs — Synthesises pre-submitted insights and prepares sectoral briefings for Day 3 — Analyses submitted national priorities post-COP and issues policy proposals — Provides MESA fellows to organise pre-thinking on national agendas — Shares monthly national briefs and the implementation pipeline for governments |
| On My Way | — The action and accountability platform on which all hub outputs are posted publicly — Where government decision-makers are named in open requests — and where they can respond — Where monitoring commitments are logged, baselined, and updated throughout the year — Shares monthly results and proposed programmes to enhance MESA proposals |

STAKEHOLDERS AND THEIR ROLES

| ACTOR | ROLE BEFORE THE Z-COP | ROLE DURING & AFTER |
| --- | --- | --- |
| The Global Call | Deploys national insight collection across 170+ countries. Coordinates focal points and contributors. Publishes pre-COP insight reports. Pipeline works to solidify partners across countries. | Amplifies hub action pages. Connects hubs to peer networks. Hosts relay session post-HLPF. Shares monthly national leadership updates. |
| MESA Institute | Sends structured policy asks to hubs. Synthesises pre-submitted insights. Prepares sectoral briefings for Day 3. MESA fellows organise pre-thinking on national agendas. | Analyses submitted priorities. Issues policy proposals. Provides technical follow-up. Shares monthly national briefs and implementation pipeline for governments. |
| On My Way | Activates accounts for all participants pre-COP. Maps multilateral engagement levels. Hosts the provisional maps visible to peer delegations overnight. | Receives and publishes all hub action items and open requests. Tracks monitoring commitments throughout the year. Shares monthly results and proposed programmes to enhance MESA proposals. |
| National Focal Points | Map local organisations and youth bodies. Submit national insights. Recruit and confirm hub participants. Activate On My Way accounts. | Facilitate daily workshops. Post all hub outputs to platform. Drive 21-day activation. Post daily updates. |
| Youth Organisations | Share contextual insights via Global Call survey. Review MESA pre-briefs. Identify priority themes from 15-theme catalogue. | Lead workshops (organisation leaders only). Own action items. Execute 21-day plan and one-year programme. |
| Government Bodies | Provide insights on existing youth policy landscape. Confirm multilateral engagement levels on platform ahead of Z-COP. Share their network to support programme scale. | Named decision-makers respond to open requests. Engage on sectoral asks. Participate in post-COP relay. Eventually support financially and share network for scale. |

PRE-Z-COP PREPARATION — THE CRITICAL PATH

The Z-COP does not work if hubs arrive without pre-submitted insights, unmapped organisations, or unactivated platform accounts. The preparation timeline below is the minimum viable path. Focal points are accountable for every item.

| PHASE | WHAT MUST HAPPEN |
| --- | --- |
| 3 monthsbefore(~June 2026) | The Global Call asks distributed to focal points. Global Call insight survey open across all participating countries. Focal points and contributors confirmed. Thematic hub subscriptions promoted and managed to ensure coordination readiness on event days. Pipeline work begins to solidify partners across countries. Initial government contacts identified per sector. |
| 2 monthsbefore(~July 2026) | Organisation and youth body mapping complete — recorded on On My Way. Government insight submissions received. National priority shortlist drafted: 3 priority areas, each with at least 3 candidate programmes aligned to the SDGs and sustainable development. Intense communication work to gather insights for every country. Comms framing that this will lead to national brainstorms through MESA and On My Way with government support. MESA fellows organise pre-thinking on national agendas. Youth councils mapped everywhere. |
| 1 monthbefore(~August 2026) | On My Way accounts activated for all participants. Multilateral engagement levels mapped on platform. Every supporting youth organisation confirms role across programme themes. Hub participants briefed on platform use and workshop format. National teams have prepared logistics and all organisations are invited. Government focal contacts confirmed per sector. Pre-submitted insights reviewed and shared across peer delegations. |
| 2 weeksbefore(~Aug 17) | All participant accounts active and tested. Peer delegations' provisional maps visible on platform. Final logistics confirmed. MESA fellows have completed national agenda pre-thinking and briefed focal points. Day 0 agenda shared with all hub participants. |
| Day before(Aug 29) | All pre-submitted insights reviewed by focal point. Hub logistics confirmed. Participants have reviewed peer delegations' provisional maps already visible on platform. Day 0 agenda confirmed with all participants and organisations. |

WHAT THE Z-COP PRODUCES — AND WHAT COMES AFTER

This is not a list of aspirations. Each item below is a posted, public, trackable entry on On My Way. If it is not on the platform, it did not happen.

| OUTPUT | DESCRIPTION |
| --- | --- |
| Nationalaction page | Three national priorities, each supported by at least three programmes, publicly visible on On My Way and aligned to the SDGs and sustainable development goals. National programmes already in existence are also mapped and visible on the page. Refined incrementally across Days 0–4 and scaled after. Not a declaration — a live, trackable commitment structure that grows with the programme. |
| Governmentengagement plan | Proposals mapped by institutional level (local, national, multilateral). Named decision-makers, leverage points, and open requests governments can respond to directly on the platform — all linked to SDG targets. Pre-COP: governments share insights. Post-COP: they measure engagement and eventually support financially, sharing their networks to scale the programme. |
| 21-day activation+ 1-yearprogramme | The immediate activation item: specific, named, verifiable, launched at Day 4 closing plenary. The one-year programme: at least three priorities with at least three programmes each, aligned to sustainable development goals, with self-financing logic. The 21-day activation is designed to create a habit of committed, tracked action. |
| Peer partnershiprequest | A joint deliverable logged on the platform with a matched peer country. Due within 10 days of COP closing. Visible to all delegations. |
| Monitoringcommitments | Trackable throughout the year alongside leadership scaling and other hub developments. Linked to SDG indicators where applicable. |
| Monthly insightspipeline | The Z-COP shares a monthly recap across all three platforms: The Global Call shares updates on national leadership. MESA shares national briefs by month and the implementation pipeline for governments. On My Way shares results and proposed programmes to enhance MESA proposals. |

Post-COP: each hub reports back publicly — what launched, what scaled, what changed, what failed. This relay session is the accountability moment. Date confirmed after HLPF. Sustained execution against the programme of priorities posted on Day 4 follows: self-financing pathway active, monitoring indicators updated, new priorities integrated as the programme evolves.

THE FOUR THEMES — ONE ARC, FOUR SCALES

Each day of the Z-COP works through one theme. The themes are not independent — they build. Self creates the individual foundation. Community creates the collective infrastructure. Institutions provide the lever for scale. Systems is where structural change becomes real. The idea is that to change systems, we need to change ourselves — and these themes are the lens through which that change is examined. The programmes produced each day are the practical expression of that reflection: each theme reveals a category of problems affecting sustainable development, and the work is to design programmes that address those problems in the country's specific context.

| DAY & THEME | SCALE · WHAT THE DAY IS LOOKING FOR |
| --- | --- |
| Day 1 · Aug 31SELFCourage, Agency & Leadership | Scale: Individual · Family · Immediate relationships · Formal youth leadership rolesThe day examines what — at the level of the individual — is preventing young people from acting on sustainable development challenges in their country. What structural, cultural, or economic conditions produce disengagement, cynicism, or paralysis? What programmes could be designed to address those conditions and build individual agency toward SDG-relevant action? |
| Day 2 · Sept 1COMMUNITYCollective Action & Peer Networks | Scale: Neighbourhood · Local group · Youth council · Cross-country peer networkThe day examines what — at the collective level — is preventing communities from organising around sustainable development priorities. Where does collective action stall, fragment, or stay invisible to the institutions that could scale it? What programmes could be designed to strengthen community-level mobilisation toward SDG outcomes? |
| Day 3 · Sept 2INSTITUTIONSWorking Systems to Scale | Scale: Schools · Local government · Ministries · NGOs · Companies · UN bodiesThe day examines what — at the institutional level — is blocking youth from influencing the decisions that shape sustainable development in their country. Who holds power, where are the entry points, and what is the one realistic ask per sector? What programmes could be designed to shift institutional behaviour toward SDG-aligned outcomes? |
| Day 4 · Sept 3SYSTEMSTransformation & Launch | Scale: National policy · Economic structures · Cultural narratives · Global cooperationThe day examines what structural conditions — policy, economic, cultural, or global — are preventing lasting change on sustainable development priorities. What systemic reforms would most transform conditions for young people? What programmes, designed across Days 1–3, now form a coherent national portfolio aligned to the SDGs — and how does that portfolio survive a change of government? |

THE DAILY CYCLE — HOW EACH DAY IS STRUCTURED

Every day follows the same cycle. The theme changes. The structure does not. The cycle has ten sessions — each with a specific function in the pipeline. Do not improvise the structure and do not collapse sessions together. What looks like repetition across five days is accumulation.

Key principle: workshops are for organisation leaders only. Non-leaders are not excluded from the Z-COP — they participate in plenaries, contribute to media work, and engage in peer activities. But the decision-making sessions that produce platform entries are restricted to those with the authority to commit.

Three principles govern the cycle. First: the work is cumulative — nothing starts from scratch. Second: the platform is the record — if it is not on On My Way, it did not happen. Third: the pipeline must stay in sync — Morning 1 exists to confirm that The Global Call, MESA Institute, and On My Way are aligned on next steps before the day's programme begins.

THE DAILY CYCLE — SESSION BY SESSION

| TIME | SESSION | WHAT HAPPENS | PURPOSE & FACILITATOR NOTES | PIPELINE ACTION |
| --- | --- | --- | --- | --- |
| PREVIOUSEVENING | Mapping WorkshopOrg leaders only~90 min | Overnight mapping: using pre-submitted Global Call insights already on the platform, map the terrain for tomorrow's theme. — Validate what is already known against the insights — Identify gaps and prioritise — Save provisional map to On My Way — visible to peer delegations overnight — No commitment made tonight | This is not blank-page work. Pre-COP insights are the raw material. The evening workshop is the first filter. Note: What is posted tonight shapes tomorrow morning's pipeline review and programme definition. | Post provisional map to On My Way Visible to all peer delegations overnight Feeds Morning 1 review |
| MORNING 1~60 min | Pipeline Review& StakeholderConfirmation | Open by reviewing: everything posted on On My Way since the previous session. — Does what is posted make sense in the pipeline flow? — Are actions and next steps clear for The Global Call, MESA, and On My Way? — Is the distribution of work across stakeholders confirmed? — Confirm tasks and responsibilities with each stakeholder group present — Tech onboarding for any participant not yet comfortable with the platform — Correct, confirm, complete any gaps from the previous session | This session is the anchor. It tells the room that work is cumulative, the platform is the record, and the pipeline is the accountability structure. Note: If Day 0 entries are vague or missing, this becomes remediation — plan for both scenarios. The pipeline review is not optional. | All overnight posts reviewed Pipeline gaps identified Stakeholder tasks confirmed Tech onboarding completed |
| MORNING 2~60 min | Global CallInsights Session(Theme of the day) | Theme introduction: brief presentation on today's theme using Global Call insights. — Present the three dimensions of today's theme — Walk through how insights translate into a plan for the day — Open discussion: what do we see in our own contexts? — Goal is shared orientation, not convergence Feedback round: participants surface initial ideas for On My Way entries and proposals for MESA on today's topic | Different countries will be at different places on every theme — that gap is the material for the afternoon. Note: Do not go directly to solutions. The discussion here is what gives the afternoon programme definition its specificity. A rushed Morning 2 produces thin afternoon entries. | Insights flagged for On My Way Initial MESA proposals noted Feeds afternoon programme definition |
| MORNING 3~60 min | Physical Activity& Learningby Doing | Practice session: participants physically do the activities confirmed in Morning 1. — Learning by doing — not observation or theory — Activities reflect the previous day's theme (see theme substitution table) — Format varies by day: individual, pair, or group — Facilitated by a partner organisation or physical lead — pre-planned, not improvised | The body processes what the mind worked through the day before. This is an integration moment, not a break. Note: The activity must be designed in advance with a partner organisation. The facilitator here is a specialist or partner — not the workshop facilitator. | No platform action during session Attendance noted Feeds Morning 4 feedback |
| MORNING 4~45 min | ActivityFeedback &Brainstorm | Debrief: what was the impact of the activity? How could it be better? — Draft feedback: what worked, what did not, proposed changes — Changes proposed for the evening programme — not implemented immediately Brainstorm: what ideas from the session could feed MESA proposals or On My Way entries? — Opportunity to surface new programme concepts not yet on the platform | The feedback loop is what makes the physical sessions improve across the week. Changes proposed here go into the evening finalisation — not back into today. Note: Keep the brainstorm focused — what from this session is specific enough to translate into a MESA proposal or On My Way entry? | Activity feedback drafted New ideas flagged for MESA and On My Way Changes queued for evening programme session |
| LUNCH~45 min | Plan Review,Output Drafting& PartnerIdentification | Platform check: focal point confirms all morning outputs are on On My Way. — First elements of today's output package confirmed — Output packages begin to be drafted for end of day Partner identification: a parallel team identifies potential implementation partners for the day's programmes. — Who specifically needs to be named in the open request? — Outreach initiated where possible | The platform check is non-negotiable. If it is not posted, it cannot be seen by peers, cannot feed the global synthesis, and cannot be held to account. The partner identification work runs in parallel — it does not wait for the afternoon session. | All morning outputs confirmed on platform Output package draft started Implementation partners identified |
| AFTERLUNCH~75 min | Mentoring &Learning Section(Close Circles) | Mentoring session: structured around the topic of the day — peer-led, small groups. — Discussion: what does implementation look like in each context? — Implementation mentoring on the specific challenges of today's theme — Self-organised circles — facilitator creates conditions, then stays out — Partners and visiting organisations may join | This is where participants make the day's theme personal — connecting Global Call data to their own organisation's reality. Note: What surfaces here consistently becomes the most specific and credible material for the programme definition session. Facilitator notes themes without directing. | No platform output required Key themes noted by focal point for programme definition |
| AFTERNOON~90 min | ProgrammeDefinition(Global CallFramework) | Programme definition: move from the general to the specific, anchored in the Global Call framework. — Work through the process for today's activities using the Global Call insights — Each organisation leader completes the day's programme sheet: barrier, component, lead structure, 10-day step — Format each entry as an open request partners, peers, and funders can respond to — Facilitator circulates: is this specific enough for someone outside the room to respond to? — Vague entries go back — session ends when every hub has at least one action item posted | Morning 2 is what makes this session specific. The post-lunch circles are what make it honest. Do not skip either. Note: The quality filter is always the same — is this specific enough for someone outside the room to respond to? If no, it is not ready to post. | At least 1 action item posted per hub Open requests logged for gaps Output package updated |
| EARLYEVENING~60 min | Reflection& Media(Joyful) | Reflection on the day: the one space in the cycle not optimised for output. Three questions to the room: — What did we confirm today that we already knew? — What surprised us? — What changed in our thinking? Media team: captures testimonies, social content, and delegate statements — joyful and positive in tone. — Content amplified through the Global Call network overnight | This is a joyful session. Do not fill it with tasks. Let the room process what shifted. Delegates who articulate their own change of thinking become the most credible messengers for the COP's work. Note: Focal point confirms final platform entries before close. | Final platform entries confirmed Media content produced Amplified via Global Call overnight |
| EVENING~60 min | ProgrammeFinalisation& Path Design | Programme finalisation: all programmes designed during the day are complete — on paper, ready for implementation. — Each organisation's path is clear: stakeholders named, programmes ready, implementation steps confirmed — Activity feedback from Morning 4 integrated — proposed changes incorporated — Output packages completed and ready for end-of-day posting This is still a paper stage: commitments are designed and ready, but implementation begins in the days that follow. — The cycle restarts: provisional map for tomorrow's theme posted to On My Way | By the end of this session, nothing should be vague. Every organisation knows its path, its stakeholders, and its next step. Note: Reflection is for processing. This session is for finalising. Do not mix them. What is posted tonight is what peer delegations read before tomorrow morning. The cycle starts again. | All day's entries complete on On My Way Output packages finalised Tomorrow's provisional map posted Volunteering moment logged |

WHAT CHANGES EACH DAY — THEME SUBSTITUTION TABLE

The cycle is fixed. The content below is what varies by day. Use this table alongside the daily cycle table to prepare each session.

| DAY | THEME | MORNING 2 — GLOBAL CALL INSIGHTS FOCUS | MORNING 3 — PHYSICAL / LEARNING BY DOING (REFLECTS PREVIOUS DAY) | POST-LUNCH — MENTORING CIRCLE FOCUS |
| --- | --- | --- | --- | --- |
| Day 0Aug 30 | Setting the Stage | Review of all pre-submitted insights from attending delegations. Platform and pipeline orientation. Mapping of national programmes already in existence across all four theme areas. No theme yet — this session is about understanding the landscape before Day 1 opens it. | N/A — Day 0 is setup. Physical sessions begin Day 1. | N/A — Lunchtime is logistics, bilaterals, and partner identification. |
| Day 1Aug 31 | SELFCourage, Agency & Leadership | What SDG-relevant problems at the individual level are most acute in our countries — and what do Global Call insights reveal about their root causes? Where does disengagement, cynicism, or economic precarity translate into inaction on sustainable development challenges? What programme designs could address these conditions? | Physical activity reflecting Day 0: arrival, activation, presence. Movement as entry — not content. Format: individual, then pair. | Close circle: what specific problems at the individual level are most affecting sustainable development in each context? What programme ideas are already emerging from the morning? What has been tried and what failed? |
| Day 2Sept 1 | COMMUNITYCollective Action & Peer Networks | What SDG-relevant problems at the community level are preventing collective action on sustainable development — and what do Global Call insights reveal about where those blockages sit? Where does community-level organisation fail to reach the scale needed to influence policy or institutions? What programme designs could address these breakdowns? | Physical activity reflecting Day 1 SELF: individual initiative and agency through the body. Solo-to-pair format. | Close circle: what specific community-level problems are most preventing SDG progress in each context? What programme designs from the morning could be strengthened or combined? What partnerships are needed to implement them? |
| Day 3Sept 2 | INSTITUTIONSWorking Systems to Scale | What SDG-relevant problems at the institutional level are blocking youth influence on sustainable development decisions — and what do Global Call insights reveal about where institutions are most and least permeable? What programme designs could shift institutional behaviour toward SDG-aligned outcomes? | Physical activity reflecting Day 2 COMMUNITY: coordination, collective movement, interdependence. Group format. | Close circle: which institutions in each country are most relevant to the day's programme designs? What is the one realistic institutional ask per sector? What leverage points already exist — and where has access been overstated? |
| Day 4Sept 3 | SYSTEMSTransformation & Launch | What structural conditions — policy, economic, cultural, global — are most preventing sustainable development progress in our countries, and what do Global Call insights reveal about where systemic change is most feasible? How do the programme portfolios built across Days 1–3 form a coherent national response to SDG priorities? | Physical activity reflecting Day 3 INSTITUTIONS: structures, roles, the individual within a system. Constraint-based movement formats. | Close circle: does the national portfolio of three priorities and at least three programmes each represent a coherent SDG response? What is missing? What is the 21-day activation item — and what support is needed to make it real? |